**Proposed Timeline for the Implementation of**

**LD 1740 – Phase I**

* In process Preliminary review of proposed rules changes by AG.’s Office
* 10/23/2014 MHDO Board **approves** **initiating proposed** agency rule
* Not mandated Permission to *proceed* with rulemaking changes submitted to

Governor’s Office for approval *(MHDO Independent Agency)*

* 11/18/2014 MAPA forms sent to Secretary Of State’s Office for publication
* 11/26/2014 Newspaper publication date
* 12/18/2014 Public Hearing

* 12/29/2014 Deadline for public comments
* 01/05/2015 Review of *provisional adoption* of the rule changes by AG’s Office
* 02/05/2015 MHDO Board approves ***provisional adoption*** of rule changes

 (*Board must adopt 150 days from comment period deadline)*

* 02/09/2015 *Provisional Adoption* package sent to the Secretary of State’s

Office & Legislative Committee (*legislative resolve, must submitted to the Legislative Committee for review by the 2nd Friday of the new year* ***01/09/2015****)*

* \_\_\_\_\_\_\_\_\_\_ Legislative Committee Review (public hearing & work session)
* \_\_\_\_\_\_\_\_\_\_ ***Final Adoption*** of Major Substantive Rule by MHDO Board
* Not mandated Permission to ***finalize adoption*** of the rule changes from the Governor’s Office *(if changed from the original proposal)*
* \_\_\_\_\_\_\_\_\_\_ Final review of final adoption of the rule changes to the AG’s Office
* \_\_\_\_\_\_\_\_\_\_ Send adoption package to the SOS for final adoption