

Super User Group Roadmap

Lasted Updated: 12/15/2013

# Introduction

## This document outlines the roadmap for the User Group; it outlines the key activities that are anticipated as well as the anticipated outputs that will be produced over the next 12 months. The group is being asked to provide advice and make recommendations based upon their perspective as users of the data that the MHDO collects. The MHDO intends to use the insight from the group to inform its development and design decisions as it moves forward in its transformation process. The bulk of this work will be performed during the course of 10-12 meetings during 2014.

## Based on feedback provided by data users directly to MHDO, through the LD 1818 Workgroup, the Deloitte report, and the NH Institute for Health Policy and Practices Quality Assurance Findings, MHDO anticipates that the work of this group will be in the following areas: Data Availability and Timeliness, Data Elements/Structure, Data Quality, Data Release and Documentation, Data Warehouse Structure, Linking Data, and Master Indexes. Within each of these areas, MHDO will work with the group to discuss key issues, gather information to answer outstanding questions, and develop prioritized recommendations for MHDO and its contractors to make future improvements and enhancements.

# Key Outputs

During 2014, it is anticipated that the User Group will produce the following key outputs:

* Review of APCD Data Modeling Roadmap
* Prioritized recommendations for Issues in each of the seven feedback areas listed above

# Timeline

MHDO’s need for guidance will evolve over the next 12 months as new issues are identified and additional information is gathered. However, the following is a rough timeline of the anticipated activities of the User Group:

|  |  |
| --- | --- |
| Month | Major Anticipated Activities |
| January | Discussion and prioritization of Data Elements/Structure |
| February | Discussion and prioritization of Data Elements/Structure (cont) |
| March | Discussion and prioritization of Linking Data |
| April | Discussion and prioritization of Master Indexes |
| May | Discussion and prioritization of Data Warehouse structure |
| June | Discussion and prioritization of Data Availability and Timeliness |
| July | Discussion and prioritization of Data Quality |
| August | Discussion and prioritization of Data Quality (cont) |
| September | Discussion and prioritization of Data Release and Documentation |
| October | Review of APCD Data Modeling Roadmap |
| November | TBD |
| December | TBD |